## WEB APPLICATION
PLATFORM ADMIN MODULE:
User profile details | 13
Farm details | 8
Pond/Tank details | 5
Measuring parameters | 21
Seed supplier details | 13
Fish details | 5
Buyer information | 8
Feed Supplier details | 8
81

## CUSTOMER APP
CUSTOMER MOBILE APP:
Dashboard | 21
Tank/Pond demographic details | 13
Monitoring dashboard | 21
Chatbot | 13
Upgrade membership | 8
76

## STORY POINT
PHASE 1 SCOPE: | POINTS
Registration module - User name/Mail ID, Firstname,Lastname,Phone number,State,Country,Pincode,Two factor authentication,login password | 5
Login Module - Email ID/Phone number, Login password,Forget password | 5
Adding Farm details - Farm name,Number of ponds,Location,etc. | 8
Adding Pond details - Pond name, Pond dimensions,Fish type,etc. | 5
Adding test data for ammonia,nitrite and nitrate - Pond name,timestamp,etc. | 5
Adding daily feed data - Pond name,Date,Time,Feed type,Quantity of feed,etc. | 5
Adding growth details - Pond name,average weight,Time stamp,etc. | 5
Adding mortality data - Pond name,Date of death,weight,etc. | 5
Adding disease data - Pond name,Disease name, Severity of disease,etc. | 5
Add treatment details - Pond name,Date,Treatment name,etc. | 5
Farm manager dashboard - Display the measured parameters from the sensors(Temperature,PH,turbidity,DO,TDS) | 8
Farm manager dashboard - Display manually tested data(ammonia,nitrite and nitrate ) | 8
Display of disease and treatement details | 5
User story grooming | 8
Backlog grooming | 5
Bootstrap Landing Page layout | 8
Bootstrap Admin dashboard shell with fixed side bar and navigation bar | 8
Bootstrap Form layouts for entering values | 8
Total | 111

## FARM ADMIN APP
FARM ADMIN MOBILE APP:
Dashboard | 21
Tank/Pond demographic details | 13
Monitoring dashboard | 21
Add test data for ammonia,nitrite and nitrate | 13
Add growth details(kg/lbs) | 8
Daily food details | 8
Add disease and treatement details | 8
Add mortality details | 8
100

## EFFORT DETAILS
EFFORT DETAILS
WEB APPLICATION | 81
CUSTOMER APP | 76
FARM ADMIN APP | 100
TOTAL MAN DAYS | 257

## HOME PAGE
HOME (for a Farm) | LIST POND
INPUT DATA: | Display pond parameters and stability
Farm name | Add pond
Pond list
Farm settings
Add cycle
Feed(Quantity)
Feeding tray(Time)
Add sampling data(weight)
Add Harvest data
Measurement(parameters)
Treatment
Mortality data
Disease details
DISPLAY DATA:
Biomass estimation(for all ponds)
Total harvest accumulation(for all ponds)
Total feed conumption(for all ponds)
Survival rate estimation(for all ponds)
Shrimp value estimation
POND DETAILS:(for each pond)
Cultivation data
Water quality data
ACTIVE POND LIST:
Cultivation data
Water quality data

## INPUT EXCEL
DAILY DISPLAY | PER POND DISPLAY/DAILY DISPLAY
Preparation | PREPARATION | FEED
Feed | PREPARATION DATA | Feed Status
Feeding tray | Measuremets | Usage
Cultivation | Chemical test | Feed data
Treatment | Microbiology test
Laboratory | Treatement
Mortality
Harvest